## Permit Log
NextDecade — Hot Work Permit Tracker — Permit Log
Permit # | Date | Shift | Location | Activity Description | Permit Issuer | Fire Watch | Initial LEL % | Status | Closed By | Notes
HW-2026-0142 | 2026-04-14 | Day | RGLNG / Train 1 / Pipe Rack PR-04 | Cut and re-weld 4" carbon steel utility line | J. Hernandez | M. Patel | 0 | Closed | M. Patel | Routine cut, no issues. 30-min post-watch clear.
HW-2026-0143 | 2026-04-14 | Day | Contractor Laydown / Pad 7 | Grinding flange face on spool A-204 | J. Hernandez | C. Nguyen | 0 | Closed | C. Nguyen | Wind-blown cardboard near work zone — see Flash 2026-04-14.
HW-2026-0144 | 2026-04-14 | Day | RGLNG / Marine Berth MB-01 | Oxy-fuel cut on bollard reinforcement | S. Okonkwo | T. Garcia | 0 | Active |  | Active at time of report.
HW-2026-0145 | 2026-04-14 | Night | RGLNG / Train 2 / Cold Box CB-02 | Brazing on instrument tubing | S. Okonkwo | L. Brennan | 0 | Suspended |  | Suspended 23:14 — gas alarm at adjacent compressor skid.
HW-2026-0146 | 2026-04-15 | Day | Designated Hot Work Area / Shop 3 | Routine fab work — no permit required | — | — |  | n/a | — | DHWA — recorded for trend analysis only.
HW-2026-0147 | 2026-04-15 | Day | RGLNG / Train 1 / North Flare KO Drum | Welding repair on 6" drain line | J. Hernandez | M. Patel | 0 | Active |  | Active. Re-test scheduled 14:00.
TOTAL PERMITS | [6 empty] | Avg LEL %:

## Permit Detail
NextDecade — Hot Work Permit Detail — HW-2026-0143
Single-permit close-out record (referenced by Flash 2026-04-14)
Permit Number | HW-2026-0143
Date / Shift | 14-Apr-2026 / Day Shift
Location | Contractor Laydown / Pad 7
Activity | Grinding flange face on spool A-204
Permit Requester | Northstar Mechanical (contractor) — R. Vasquez
Permit Issuer | J. Hernandez (NDLNG)
Fire Watch | C. Nguyen (NDLNG, certified)
Authorized Gas Tester | C. Nguyen — calibrated 06-Apr-2026
Walkdown Completed | 09:30, 14-Apr-2026 — combustibles cleared 35 ft radius
Initial Combustible Gas Reading | 0.0% LEL
60-min Re-test | 0.0% LEL (10:42)
Risk Classification | Standard (not Elevated)
Permit Authorized | 09:42, 14-Apr-2026
Work Started | 09:51
Stop-Work Event | 10:02 — wind-borne cardboard ignition, 22 ft from work
Stop-Work Action | Fire Watch extinguished cardboard with 20-lb ABC, ~30 sec total response time
Resumption | Not resumed — work re-permitted 15-Apr-2026 with 100-ft sweep
Post-Work Watch | 30 minutes — area clear, no smoldering
Permit Closed | 10:38, 14-Apr-2026
Outcome | Near-miss — no injury, no damage, no escalation
HSSE Flash Issued | Yes — Flash 2026-04-14 (link in Tracker Notes column K)

## Trend Summary
NextDecade — Hot Work Permit Tracker — Trend Summary (Q2 2026 to date)
Week of | Total Permits | Closed | Suspended | Near-Misses | Incidents
2026-03-30 | 38 | 36 | 2 | 0 | 0
2026-04-06 | 41 | 39 | 2 | 1 | 0
2026-04-13 | 47 | 44 | 3 | 1 | 0
QUARTER TO DATE
Notes:
• Suspensions and near-misses are trending up with construction activity. Apr 14 near-miss prompted procedural change (100-ft wind-blown sweep). Re-evaluate at next monthly HSSE review.