BOARD MEMORANDUM

| TO: | Board of Directors, NextDecade Corporation |
| --- | --- |
| FROM: | Matt Schatzman, Chairman and Chief Executive Officer |
| DATE: | April 15, 2026 |
| SUBJECT: | Q1 2026 Rio Grande LNG Construction Progress and Phase 2 FID Readiness |

## Executive Summary

Rio Grande LNG Phase 1 construction advanced to 68% complete through March 31, 2026, consistent with the schedule presented to the Board at the February 2026 meeting. First LNG remains targeted for the second half of 2027. The Phase 2 Final Investment Decision package is on track for Board consideration in the third quarter of 2026. No material safety events occurred during the quarter.

## Construction Status

Engineering is 99% complete. Procurement is 88% complete with all long-lead equipment on site or in transit. Construction is 52% complete across Trains 1, 2, and 3. The liquefaction cold box for Train 1 was set during the quarter without incident; commissioning of the non-cryogenic utilities is scheduled to begin in July 2026.

## Commercial and Regulatory

Long-term SPAs for Phase 2 volumes are progressing with three investment-grade counterparties. The FERC authorization for Phase 2 remains in effect; the Department of Energy non-FTA export authorization is expected to be confirmed in the second quarter of 2026. There have been no changes in the regulatory posture previously disclosed to the Board.

## Financial

Phase 1 remains on budget at $18.4 billion. As of March 31, 2026, total project spend was $9.8 billion, funded from the project debt facility ($6.2B), committed equity ($3.0B), and the corporate revolver ($0.6B). The Company's liquidity position provides adequate headroom through first LNG.

## Safety and HSSE

The site recorded 3.1 million construction hours in the quarter with a Total Recordable Incident Rate of 0.42, below the industry benchmark of 0.65. No Life-Saving Rule violations were recorded. One near-miss event related to hot work (HW-2026-0143, April 14) was investigated; corrective actions are complete and will be discussed in the HSSE Committee pre-read.

## Phase 2 Readiness

Management recommends the Board direct the preparation of a formal Phase 2 FID package for consideration at the August 2026 meeting. Items that must be resolved prior to FID include:

Final SPA execution with the three anchor offtakers.

Phase 2 debt facility commitment letters.

Updated EPC cost certainty from the primary contractor.

Confirmation of Phase 2 incremental equity funding.

Board-level review of community and stakeholder engagement metrics in the Rio Grande Valley.

## Recommended Board Action

The Board is asked to (i) acknowledge receipt of this report, (ii) authorize management to prepare the Phase 2 FID package for the August 2026 meeting, and (iii) direct the HSSE Committee to review the HW-2026-0143 corrective action plan at its May 2026 session.

Respectfully submitted,

Matt Schatzman

Chairman and Chief Executive Officer, NextDecade Corporation