OFFICE OF THE CEO

From:  Matt Schatzman <matt.schatzman@next-decade.com>

To:  All NextDecade <allnextdecade@next-decade.com>

Sent:  April 15, 2026  3:30 p.m. Central

Subject:  Q1 check-in - 68%, safety, and what's next

Team,

Quick update as we close out Q1 2026. Rio Grande LNG Phase 1 is now 68% complete. That's a real milestone, and it's because of the work every one of you is doing. Thank you.

### Where we are on construction

Engineering is basically done (99%). Procurement is almost there (88%). Construction is 52% across all three trains. The Train 1 cold box went up this quarter without incident - nothing routine about that, and it's a huge win for the commissioning team.

First LNG is still on track for the second half of 2027. We're going to keep that commitment.

### Safety - we're doing well, and we can do better

Our TRIR for the quarter was 0.42, better than the industry benchmark of 0.65. That's great, and we want to keep it that way.

We had a hot-work near-miss on April 14 - HW-2026-0143. Nobody was hurt, but a fire watch was relieved without a formal handoff. We've already closed that gap in our procedure. The reminder: every permit, every handoff, every time. If something doesn't feel right, stop work.

### What's next - Phase 2

Our Commercial team is advancing three long-term SPAs with investment-grade counterparties. Our FERC authorization is in place. We're targeting a Phase 2 Final Investment Decision in the second half of this year. That's a big deal for this company and for the Rio Grande Valley.

### People news

We welcomed 47 new teammates in Q1 - introduce yourself.

Two teammates hit their 5-year anniversary this month.

Benefits open enrollment kicks off in May.

The next NEXT Digest drops Friday.

If you've got questions, send them to allhands@next-decade.com before the town hall on the 18th. See you then.

Matt

Matt Schatzman
Chairman and CEO, NextDecade Corporation