## Summary
Rio Grande LNG - Construction KPI Dashboard
Period ending March 31, 2026 ¦ Data as of April 15, 2026
Construction % Complete | TRIR (Rolling 12 mo.) | Project Spend ($B) | Schedule Confidence
68% | 0.42 | $9.8B | High
Target 67% - ahead by 1 pt | Below industry benchmark 0.65 | Budget: $18.4B total - 53% | First LNG: 2H 2027

## Progress by Area
Rio Grande LNG - Progress by Area
All values in percent complete
Area | Engineering | Procurement | Construction | Status
Train 1 | 100 | 96 | 72 | On track
Train 2 | 100 | 92 | 55 | On track
Train 3 | 99 | 82 | 34 | On track
Common Utilities | 100 | 98 | 78 | On track
Storage Tanks | 100 | 95 | 62 | On track
Marine / Jetty | 98 | 72 | 38 | Monitor
Feed Gas Pipeline | 100 | 99 | 88 | On track

## HSSE Trend
HSSE - 12 Month Trend
TRIR = Total Recordable Incident Rate (per 200,000 hours)
Month | Hours (M) | Recordables | TRIR
Apr 2025 | 2.4 | 6 | 0.5
May 2025 | 2.5 | 5 | 0.4
Jun 2025 | 2.6 | 7 | 0.54
Jul 2025 | 2.8 | 6 | 0.43
Aug 2025 | 2.9 | 5 | 0.34
Sep 2025 | 3 | 7 | 0.47
Oct 2025 | 3 | 6 | 0.4
Nov 2025 | 2.9 | 5 | 0.34
Dec 2025 | 2.7 | 6 | 0.44
Jan 2026 | 2.9 | 7 | 0.48
Feb 2026 | 3 | 6 | 0.4
Mar 2026 | 3.1 | 7 | 0.45
TOTAL / Avg